## Overview
Aster Health UAT
Execution not started
Execution status | Case count | UAT scope | Baseline | Readiness note
Not Started | 26 | Plan search through results and per-plan handoff | BRD/PRD/FRD/SRS v0.1 | Enrollment pages and completion remain out of scope.
Passed | 0 | Current status | Not executed | All test cases begin as Not Started; record actual outcomes during UAT.
Failed | 0 | Open decision dependencies | D-01 to D-07 | Tests depending on unresolved rules must remain blocked until approved.
Blocked | 0 | Test data | Synthetic only | Do not enter real member or health information.
Not Applicable | 0
Total cases | 26
Run instructions
1. Resolve readiness gates on the Readiness tab before scheduling execution.
2. Execute cases on Test Cases and select a status from the dropdown.
3. Record actual result, defect ID, evidence link, tester, and run date.
4. Re-test fixes without erasing the original defect history; link retest evidence in the same case or defect record.
5. Use the Word UAT Plan for entry/exit criteria, role guidance, and sign-off.

## Test Cases
UAT
Unexecuted cases
Test ID | Journey area | Scenario | Priority | Preconditions / test data | Test steps | Expected result | Traceability | Decision dependency | Execution status | Actual result | Defect ID | Evidence link | Tester | Run date
UAT-01 | Entry | Open plan search from an authenticated Aster Health app session | P0 | Test member account; approved test build; signed-in state. | 1. Sign in with the test account. 2. Open the approved plan-search entry. | Plan-search criteria screen opens. Sign-in and account recovery remain outside this module. | BO-01; SYS-001; SM-01 | — | Not Started
UAT-02 | Location validation | Submit without State | P0 | Criteria screen open; no State selected. | 1. Leave State blank. 2. Complete other required fields. 3. Submit search. | Submission is blocked; State is identified; valid entered values remain available for correction. | SYS-002/003; GA-02; SM-02 | — | Not Started
UAT-03 | Location validation | Submit without City | P0 | Criteria screen open; approved State selected. | 1. Leave City blank. 2. Complete other required fields. 3. Submit search. | Submission is blocked; City is identified; valid values remain available. | SYS-002/003; GA-02; SM-02 | — | Not Started
UAT-04 | Location validation | Submit without the approved third geography | P0 | D-01 resolved; approved geography catalogue loaded. | 1. Leave County or Country blank, as approved. 2. Complete remaining criteria. 3. Submit. | Submission is blocked and the approved third geography field is identified. | SYS-002/003; GA-02; D-01; SM-02 | D-01 | Not Started
UAT-05 | Location selectors | Verify selector dependency and valid geographic combination | P1 | D-01 resolved; location test fixture includes valid and invalid combinations. | 1. Select State. 2. Inspect available City and third-geography values. 3. Select a valid combination. 4. Change the parent location. | Child options follow the approved hierarchy; stale dependent values clear or update per approved rule. | SYS-002/003; IF-UI-01; GA-02; SM-02 | D-01 | Not Started
UAT-06 | Plan type | Verify approved plan-type values and selection behavior | P0 | D-02 resolved; approved plan-type list available. | 1. Open plan-type control. 2. Verify approved values. 3. Apply required/default/single-or-multi-select behavior. | Displayed values and selection behavior match the approved catalogue and rule; request includes the selected identifiers. | SYS-004; IF-GDS-01; GA-03; SM-03 | D-02 | Not Started
UAT-07 | Essential benefits | Select and deselect multiple essential benefits | P0 | D-02 resolved; at least three approved benefits available. | 1. Select two or more benefits. 2. Deselect one. 3. Submit a valid search. | Multiple selection is supported; active benefit identifiers are included; deselected identifier is excluded. | SYS-005; IF-GDS-01; GA-04; SM-04 | D-02 | Not Started
UAT-08 | Essential benefits | Verify plan matching for selected benefits | P0 | D-02 resolved; fixtures include plans matching all, some, and none of selected benefits. | 1. Select the agreed combination. 2. Search. 3. Compare returned plans with expected fixture outcomes. | Returned plans follow the approved all/any/other matching semantics and do not contradict the approved benefit rule. | SYS-005/008; GA-04; SM-04 | D-02 | Not Started
UAT-09 | Search integration | Submit valid criteria to the approved plan-data source | P0 | D-03 resolved; integration test environment and request/response contract available. | 1. Enter valid approved criteria. 2. Submit once. 3. Review service/integration evidence for the request. | Canonical geography, plan-type, and benefit identifiers are sent using the approved contract; request is traceable. | SYS-006/008; IF-GDS-01/03; GA-05; SM-05 | D-03 | Not Started
UAT-10 | Results | Verify plan fields and cost-sharing against source records | P0 | D-04 resolved; fixture has approved names, type, benefits, cost-sharing units and source values. | 1. Search for matching fixture plans. 2. Compare each displayed field to the expected source record. | Plan name, type, benefits and cost-sharing match approved definitions, labels, units and source values. | SYS-008/009; IF-GDS-02/05; GA-06; SM-06 | D-04 | Not Started
UAT-11 | Plan details | Open selected plan details and return to results | P1 | D-04 resolved; at least two distinguishable plan fixtures. | 1. Open details for Plan A. 2. Confirm plan identity. 3. Return to results. | Selected plan is clear; return behavior and retention of criteria/results match approved Product behavior. | SYS-010/011; GA-07; SM-06 | D-04 | Not Started
UAT-12 | No match | Handle a valid search with zero matching plans | P1 | D-06 resolved; source fixture returns valid empty result. | 1. Submit criteria that return no plans. 2. Review the result state. 3. Revise criteria and search again. | App displays approved no-match state, distinguishes it from error, and allows criteria revision/resubmission. | SYS-016; IF-GDS-04; GA-10; SM-09 | D-06 | Not Started
UAT-13 | Source failure | Handle timeout or unavailable plan-data source | P1 | D-06 resolved; controllable timeout/unavailable-source fixture. | 1. Submit valid criteria. 2. Simulate the approved source failure. 3. Review message and retry path. | Failure is not shown as no-match; approved recovery is available; criteria retention follows approved behavior. | SYS-017/020; IF-GDS-03/04; GA-10; SM-09 | D-06 | Not Started
UAT-14 | Source failure | Handle malformed or partial plan response | P1 | D-06 resolved; response fixtures for malformed and partial data. | 1. Submit valid criteria. 2. Return malformed/partial fixture. 3. Inspect results and error state. | System follows approved partial-result policy and never labels unusable source data as a valid no-match. | SYS-017; IF-GDS-04; GA-10; SM-09 | D-06 | Not Started
UAT-15 | Search recovery | Retry, preserve criteria, and prevent unintended duplicate submission | P1 | D-06 resolved; test build has progress state and retry behavior. | 1. Submit valid criteria during a delayed response. 2. Attempt a second submission. 3. Trigger retry after a failure. | Progress is indicated; duplicate behavior follows the approved rule; criteria are retained where approved. | SYS-007/017/020; GA-10; SM-09 | D-06 | Not Started
UAT-16 | Phone handoff | Verify each result uses its own representative number | P0 | D-05 resolved; at least two test plans with distinct safe test numbers. | 1. Search for Plan A and Plan B. 2. Activate Talk to a Representative on each row. 3. Inspect phone handler destination. | Each action passes only the number associated with that plan row; no cross-plan number substitution occurs. | SYS-012/013/018; GA-08; SM-07 | D-05 | Not Started
UAT-17 | Phone handoff | Cancel device phone confirmation and return to the app | P1 | D-05 resolved; supported device/OS and safe test number. | 1. Activate a representative link. 2. Cancel the device phone confirmation. 3. Return to the app. | App returns according to approved platform behavior; selected plan and search context remain clear. | SYS-013; GA-08; SM-07 | D-05 | Not Started
UAT-18 | Phone handoff | Handle missing or invalid representative number | P1 | D-05 resolved; fixtures for missing and invalid numbers. | 1. Open a result with missing/invalid phone data. 2. Activate or inspect the call action. | Approved fallback is shown; no other plan’s number is used; member is not sent to an unrelated number. | SYS-018; GA-08; SM-07 | D-05 | Not Started
UAT-19 | Enrollment handoff | Verify Enroll link opens the selected plan destination | P0 | D-05 resolved; at least two test plans with distinct approved test URLs. | 1. Search for two plans. 2. Activate Enroll for one plan. 3. Verify the destination identifier. | The link maps to the same plan selected in the result; no other plan’s destination is used. | SYS-014/015; GA-09; SM-08 | D-05 | Not Started
UAT-20 | Enrollment handoff | Handle unavailable or invalid plan destination | P1 | D-05 resolved; fixtures include missing, invalid and expired test destinations. | 1. Inspect a plan with an unavailable destination. 2. Activate or inspect Enroll. | Approved fallback is shown; invalid destination is not silently replaced with a different plan URL. | SYS-018; GA-09; SM-08 | D-05 | Not Started
UAT-21 | Scope boundary | Confirm module ends at external enrollment hyperlink | P0 | D-05 resolved; test destination available. | 1. Activate Enroll. 2. Observe navigation boundary and module behavior. | A plan-specific external handoff opens; no enrollment form, enrollment decision, or completion state is implemented in this module. | SYS-014/015; GA-09; SM-08 | — | Not Started
UAT-22 | Helpdesk | Verify approved Helpdesk placement and route, if retained | P2 | D-07 resolved; approved route and test-safe channel available. | 1. Open the approved entry point. 2. Select Helpdesk if retained. 3. Verify route and return behavior. | Helpdesk appears only in the approved boundary and opens the approved channel; if excluded, no in-scope entry is shown. | SYS-019; GA-12; SM-10 | D-07 | Not Started
UAT-23 | Accessibility | Verify accessible names and states for key controls | P1 | Approved accessibility criteria and assistive technology/device setup available. | 1. Navigate criteria, validation, results and plan actions with approved assistive technology. 2. Inspect labels and state announcements. | Controls expose approved accessible names/states; required, invalid, pending, no-match and error states are perceivable. | IF-UI-02/04; GA-11; SM-11 | D-06 | Not Started
UAT-24 | Privacy and data handling | Verify test data, logging and retention behavior | P1 | D-06 resolved; security/privacy test expectations and logging evidence access approved. | 1. Use only synthetic test member/plan data. 2. Search and trigger an error. 3. Inspect approved logs for necessary fields and prohibited sensitive data. | Only approved search data is handled/logged; retention and access follow the approved privacy/security rules. | SEC / OPS requirements; GA-11; SM-11 | D-06 | Not Started
UAT-25 | Supported platforms | Verify key journey and handoffs on supported iOS and Android versions | P1 | Supported OS/device matrix approved; test devices/builds available. | 1. Run entry, search, results, phone link, and enrollment link on each agreed platform. | Layout and platform handoffs meet approved behavior on each supported device/OS combination. | IF-UI-05; GA-11; SM-11 | D-06 | Not Started
UAT-26 | Analytics | Verify approved success and support events are captured | P2 | D-07 resolved; analytics event catalogue and test dashboard/log access approved. | 1. Complete a search, no-match, phone handoff, and enrollment handoff. 2. Inspect approved event evidence. | Agreed events carry approved identifiers and do not imply enrollment completion when only a handoff occurred. | BO-01–05; GA-01/13; SM-11 | D-07 | Not Started

## Readiness
Readiness
Resolve gates before UAT.
Decision ID | Approval needed | Proposed owner | Related cases | Status | Approver | Decision date | Notes / evidence
D-01 | Choose County or Country; approve location hierarchy and catalogue. | Product Owner + Plan Data Owner | UAT-04, UAT-05 | Open
D-02 | Approve plan-type values/rules and essential-benefit catalogue/matching semantics. | Product Owner + Plan Data Owner | UAT-06, UAT-07, UAT-08 | Open
D-03 | Confirm authoritative GDS/system, partner identity, and test interface contract. | Sponsor + Integration Lead | UAT-09 | Open
D-04 | Approve plan/detail fields, cost-sharing definitions/units, freshness, and missing-data handling. | Plan Data Owner + Product Owner | UAT-10, UAT-11 | Open
D-05 | Approve phone and enrollment destinations, device confirmation, fallback, and link health. | Member Services + Enrollment Owner | UAT-16 to UAT-21 | Open
D-06 | Approve error/retry/offline rules, supported platform matrix, accessibility and privacy criteria. | Product + Integration + QA + Security | UAT-12 to UAT-15, UAT-23 to UAT-25 | Open
D-07 | Decide Helpdesk boundary, operational model, analytics events, and success measures. | Product + Member Services + Sponsor | UAT-22, UAT-26 | Open
Environment gate | Evidence required | Owner | Status | Approver | Date | Evidence link | Notes
Approved baseline | Approved expected behavior for in-scope requirements and decisions. | Product Owner | Not Ready
Test build | Build/version deployed in a test environment and release notes available. | QA / Engineering | Not Ready
Test accounts | Test identities and roles available; no real member data. | UAT Coordinator | Not Ready
Test data | Synthetic match/no-match/edge and plan destination fixtures with expected outputs. | Plan Data Owner | Not Ready
External test destinations | Safe test endpoints/numbers or controlled handoff behavior. | Enrollment / Member Services | Not Ready
Defect and evidence process | Defect tool, severity agreement, access and evidence location confirmed. | QA Lead | Not Ready